## Interactable Characters
Category | Asset | Not Started/Assigned To | In progress | Committed | Implemented | Sign-Off
Knight / Player
Sprites | sprite_knight_body | jade
| sprite_knight_legs | jade
| sprite_knight_helmet | jade
| sprite_knight_sword | jade
Flies
Sprites | sprite_fly_small_body | jade
| sprite_fly_king_body | jade
| sprite_fly_small_wings | jade
| sprite_fly_king_wings | jade
| sprite_fly_small_green particles | jade
| sprite_fly_king_green particles | jade
| sprite_fly_small_white particles | jade
| sprite_fly_king_white particles | jade
Prefabs | prefab_knight | max (nathan maybe)
| prefab_fly_small | max (nathan maybe)
| prefab_training dummy | max (nathan maybe)
| prefab_fly_king | max (nathan maybe)

## Background
Category | Asset | Not Started/Assigned To | In progress | Committed | Implemented | Sign-Off
During Game
Sprites | sprite_tree_[#] | jade
| sprite_bush_[#] | jade
| sprite_mountains_[#] | jade
| sprite_grass_[#] | jade
| sprite_cloud_[#] | jade
| sprite_windmill_body | jade
| sprite_windmill_sails | jade
| sprite_windmill_door | jade
| sprite_health bar | jade
| sprite_wagon | jade
| sprite_practice dummy | jade
| sprite_flower_tall_yellow | jade
| sprite_flower_rectangle_red | jade
| sprite_flower_tall_yellow_double | jade
| sprite_flower_square_blue | jade
| sprite_flower_circle_purple | jade
| sprite_flower_circle_red | jade
Sounds | sound_grass_ruffle | max
| sound_crickets | max
| sound_chirping | max
| sound_walking | max
| sound_hitting | max
| sound_breaking_dummy | max
| sound_taking damage | max
| sound_player_death | max
| sound_jumping | max
| sound_windmill_door | max
Home Screen
Sprites | sprite_fly | jade | jade
| sprite_flower_tall_yellow | jade | jade
| sprite_flower_circle_yellow | jade | jade
| sprite_flower_square_blue | jade | jade
| sprite_flower_circle_purple | jade | jade
| sprite_flower_circle_red | jade | jade
| sprite_button_yellow | jade | jade
Sounds | sound_button | max
| sound_fly | max
| sound_music | max
Death Screen
Sprites | sprite_button | jade
Sounds | sound_music | max
| sound_button | max
End Screen
Sprites | sprite_button | jade
Sounds | sound_music | max
| sound_button | max
Script | (home screen) "Fly Slayer" | nathan
| (death screen) "Game Over" | nathan
| (death screen) "Try Again" | nathan
| (in game) "Health" | nathan
| (end screen) "The End" | nathan
| (end screen) "Replay" | nathan
Prefabs | prefab_tree_[#] | max (nathan maybe)
| prefab_bush_[#] | max (nathan maybe)
| prefab_mountain_[#] | max (nathan maybe)
| prefab_windmill | max (nathan maybe)